## Instructions
Instructions
Password protection for sheet and workbook to protect formulas is: 1234
Cost estimates
Understand the layout | Take a moment to familiarize yourself with the layout of the spreadsheet. You'll notice columns for different categories of information, including task details, resource quantities, unit costs, and calculated costs.
Fill in direct cost task details | In the "Item name" column, list the tasks or work packages that make up your project. These could be specific project activities, deliverables, or milestones.
Identify direct cost resource requirements | Move to the columns corresponding to each resource (e.g., labor). For each task, enter the quantity of each resource required. Use consistent units of measurement (e.g., hours, kilograms, units) to ensure accuracy.
Gather direct cost resource costs | In the columns designated for "Bill rate", enter the cost per unit for each resource. This information can be obtained from reliable sources, such as historical records, vendor quotes, or industry standards.
Calculate resource costs | The spreadsheet will automatically calculate the estimated cost of each resource for each task by multiplying the quantity with the unit cost. Ensure that the calculated costs reflect accurate estimations.
Sum up direct costs | The "Total direct cost" column will automatically sum up the costs of all resources for each task, providing the direct cost estimate for that task.
Include other direct costs | If applicable, add any other direct costs in the designated rows and columns. These could include software, hardware, and other non labor costs that contribute to the project's overall cost.
Include Indirect Costs | If applicable, add any indirect costs in the designated rows and column. These could include overhead, administrative expenses, and other costs that contribute to the project's overall cost.
Allocate Contingency | Enter the percentage of contingency you wish to allocate in the "Contingency" column. The spreadsheet will calculate the contingency amount based on the costs. 1 = no risks associated with task or other direct or indirect costs finishing on time/budget/scope 1.1 = low risk associated with task or other direct or indirect costs resource finishing on time/budget/scope 1.2 = medium risk associated with task or other direct or indirect costs resource finishing on time/budget/scope 1.3 = high risk associated with task or other direct or indirect costs resource finishing on time/budget/scope
Review and Validate | Before finalizing, review your entries for accuracy. Ensure that quantities, unit costs, and calculations are correct. Seek input from stakeholders or experts if needed.
Generate Total Estimate | The "Adjusted est. costs" column will automatically calculate the total estimated cost for each task, including direct costs, indirect costs, and contingency.
Monitor and Update | As your project progresses, continuously monitor actual costs and compare them to the estimates. Update the spreadsheet accordingly to maintain accuracy.

## Cost estimates
Cost Estimates
| Total budget: |  | 125000
| Total estimates: |  | 127428.5
| Total remaining: |  | -2428.5
| Level | WBS code | SOW reference | Item name | Role | Project Manager | Project Coordinator | Sponsor | Strategist | Support Strategist | TBD | TBD2 | TBD3 | Basis of estimates | Contingency | Est. hours | Adjusted est. hours | Est. costs | Adjusted est. costs | Additional notes
[5 empty] | Name | Jane | Sam | Susan | John | Bill | TBD | TBD | TBD
| Direct costs (hourly) |  |  |  | Bill rate | 150 | 190 | 250 | 300 | 320 | 100 | 100 | 200
| 4 | 1.1.1.1 | Phase 1 - Concept proposal - TOC | Draft TOC | Jane: 1; Sam: 1; John: 16 | Based on prior TOC draft effort | 1.3 | 18 | 23.4 | 5140 | 6682
| 4 | 1.1.1.2 | Phase 1 - Concept proposal - TOC | Review TOC | Jane: 1; Sam: 1; Susan: 1.5; Bill: 1.5 | Based on prior TOC review effort; 1.5 hours each reviewer | 1.1 | 5 | 5.5 | 1195 | 1314.5
| 4 | 1.1.2.1 | Phase 2 - Concept proposal - Target audience | Draft target audience | Jane: 1; Sam: 1; John: 8 | Based on prior target audiences draft effort | 1.2 | 10 | 12 | 2740 | 3288
| 4 | 1.1.2.2 | Phase 2 - Concept proposal - Target audience | Review target audience | Jane: 1; Sam: 1; Susan: 0.5; Bill: 0.5 | Based on prior target audiences review effort; .5 hours each reviewer | 1.1 | 3 | 3.3 | 625 | 687.5
| 4 | 1.1.3.1 | Phase 3 - Concept proposal - Proposed components | Draft propose components | Jane: 1; Sam: 1; John: 16 | Based on prior proposed components draft effort | 1.3 | 18 | 23.4 | 5140 | 6682
| 4 | 1.1.3.2 | Phase 3 - Concept proposal - Proposed components | Review proposed components | Jane: 1; Sam: 1; Susan: 1.5; Bill: 1.5 | Based on prior proposed components review effort; 1.5 hours each reviewer | 1.1 | 5 | 5.5 | 1195 | 1314.5
| 4 | Etc. | [13 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
[16 empty] | 0 | 0 | 0 | 0
| Total direct costs (hourly) |  |  |  |  | 6 | 6 | 3.5 | 40 | 3.5 | 0 | 0 | 0 |  |  | 59 | 73.1 | 16035 | 19968.5
Other direct costs (hardware, software, tools, etc.)
| 1 | 1 | Project name | Computer (one-time purchase) | 2000 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 5 | 5 | 10000 | 10000
| 1 | 1 | Project name | PM software (monthly service) | Name: 30; Jane: 1; Sam: 1 |  | 1 | 2 | 2 | 60 | 60
| 4 | 1.1.3.2 | Phase 3 - Concept proposal - Proposed components | Travel (per trip) | Name: 1000; Jane: 1; John: 1 |  | 1.2 | 2 | 2.4 | 2000 | 2400
[16 empty] | 0 | 0 | 0 | 0 | bar: Name
[16 empty] | 0 | 0 | 0 | 0 | bar: Name
[16 empty] | 0 | 0 | 0 | 0 | bar: Name
[16 empty] | 0 | 0 | 0 | 0 | bar: Name
| Total ODCs | [14 empty] | 9 | 9.4 | 12060 | 12460 | 0
Indirect costs (overhead, administration, benefits, etc.)
| 1 | 1 | Project name | Admin staff salaries | Name: 45000; TBD: 1 |  | 1 | 1 | 1 | 45000 | 45000
| 1 | 1 | Project name | HR staff salaries | Name: 50000; TBD: 1 |  | 1 | 1 | 1 | 50000 | 50000
[16 empty] | 0 | 0 | 0 | 0 | bar: Name
[16 empty] | 0 | 0 | 0 | 0 | bar: Name
[16 empty] | 0 | 0 | 0 | 0 | bar: Name
| Total IDCs | [14 empty] | 2 | 2 | 95000 | 95000 | 0 | bar: Name
| Total project estimates | [16 empty] | 123095 | 127428.5