## Instructions
Instructions
Password protection for sheet and workbook to protect formulas is: 1234
Work Breakdown Dictionary (WBD)
Level | Add the level of the task from the WBS
Work Breakdown Structure (WBS) code | Add the WBS code for the task from the WBS
Item name | Add the name of the task from the WBS
Definition | Add the description for the task
Owner | Add the team member who is responsible for completing the task
Dependencies | Add any dependencies for the task
Assumptions and constraints | Add any assumptions and constraints for the task
Risks | Add any risks for the task and the mitigation strategies
Schedule Network Diagram
Identify project tasks and activities | Review the WBS and WBD and identify all the individual tasks or activities required to complete the project. These activities should be specific, measurable, and defined in terms of their deliverables.
Determine task dependencies | Identify the logical dependencies between the project tasks. Determine which tasks must be completed before others can start (predecessors) and which asks can only start after certain activities are finished (successors).
Define ask durations estimates | Estimate the duration or time required to complete each task. Use historical data, subject matter expert judgment, or other estimation techniques to derive realistic timeframes for each task.
Create node diagram | Begin by drawing the nodes (boxes) on a blank sheet of paper, a spreadsheet, or a project management software tool. Each node represents an individual task from the WBS.
Establish activity sequence | Connect the nodes with arrows to represent the sequence of tasks based on their dependencies. An arrow going from Task A to Task B indicates that Task B depends on the completion of Task A.
Label dependencies | On each arrow, label the type of dependency (Finish-to-Start, Start-to-Start, Finish-to-Finish, Start-to-Finish) and any lag or lead time if applicable.
Identify critical path | Calculate the total duration of each path from the project start to the end (through the arrows). Identify the critical path, which is the longest path and determines the project's minimum duration.
Add task durations | On each node, write the estimated duration for the corresponding task.
Estimate total project duration | Sum up the durations along the critical path to estimate the total project duration. This will be the minimum time needed to complete the project.
Consider resource constraints | Review the resource availability and constraints to ensure the schedule is feasible and achievable within resource limitations.
Perform schedule compression (if necessary) | If the project duration needs to be reduced, consider schedule compression techniques like fast-tracking or crashing to optimize the critical path.
Validate with stakeholders | Share the Schedule Network Diagram with key stakeholders, team members, and decision-makers to ensure that the dependencies, sequence, and durations align with their expectations and requirements.
Update and maintain | Throughout the project, keep the Schedule Network Diagram updated to reflect changes in the project plan, new dependencies, or revised task durations.
Schedule Baseline
Create baseline schedule | Use the WBS, WBD, and Schedule Network Diagram to create the schedule baseline.
Establish milestones and deliverables | Identify key milestones and deliverables in the schedule. Milestones are significant events or achievements that help gauge project progress.
Review and analyze the schedule | Analyze the schedule for feasibility, resource allocation, and potential bottlenecks. Ensure that the project can be realistically completed within the proposed timeline.
Incorporate buffer time for review and contingency | Allow buffer time for review and adjustments before finalizing the schedule baseline to accommodate any last-minute changes or refinements.
Document and obtain approval | Document the entire schedule, including activities, durations, resources, milestones, and the critical path. Present the schedule baseline to relevant stakeholders for approval.
Clearly communicate the baseline | Ensure all team members and stakeholders are aware of the approved schedule baseline. Provide access to the baseline documentation for easy reference.
Maintain a change control process | Establish a change control process to handle any future changes to the schedule. Any modifications to the baseline should go through a formal approval process.
Update the schedule baseline (if necessary) | If significant changes in the project scope or requirements occur, evaluate the impact on the baseline. If required, update and re-baseline the schedule with appropriate approvals.
Current Schedule
Create a copy of the schedule baseline | Once the project baseline is approved, create a copy of it for your current schedule to share with the the project team.
Monitor and track progress | Regularly monitor and track progress in the current schedule against the schedule baseline. Use the schedule baseline as a reference point to identify any deviations or delays.
Maintain a change control process | Establish a change control process to handle any future changes to the schedule. Any modifications to the baseline should go through a formal approval process.

## WBD
Work Breakdown Dictionary (WBD)
| Level | WBS code | Item name | Definition | Owner | Dependencies | Assumptions and constraints | Risks
| 1 | 1 | Project name | - | -
| 2 | 1.1 | Concept proposal | deliverable | - | three months from start date |  | Possible delay with sponsor approval; add lag time to account for this
| 3 | 1.1.1 | Theory of change (TOC) | deliverable | - |  | must have approved problem statement before start
| 4 | 1.1.1.1 | Draft TOC | strategist drafts content with input from team | Strategist
| 4 | 1.1.1.2 | Review TOC | internal team reviews content and shares feedback | Sponsor, Support Strategist
| 4 | Etc. |  |  | -
| 3 | 1.1.2 | Target audience | deliverable | - |  | developed with TOC
| 4 | 1.1.2.1 | Draft target audience | strategist drafts content with input from team | Strategist
| 4 | 1.1.2.2 | Review target audience | internal team reviews content and shares feedback | Sponsor, Support Strategist
| 1 | Etc. |  |  | -
| 3 | 1.1.3 | Proposed components | deliverable | - | four to six weeks from start | must have approved TOC and audience before start
| 4 | 1.1.3.1 | Draft propose components | strategist drafts content with input from team | Strategist
| 4 | 1.1.3.2 | Review proposed components | internal team reviews content and shares feedback | Sponsor, Support Strategist
| 4 | Etc.

## Schedule Network Diagram
Schedule Network Diagram (to sequence and estimate)
| Approach used to sequence activities: | Developed with work packages
| Basis used for duration estimates: | Based on earlier XYZ project
[# duration estimates/days] Task/Sub-task
is critical path is yellow (i.e., the path with longest duration)
| minimum project duration based on critical path is: | 25 business days
[5] 1.1.1.2 Review TOC
| Start |  | [10] 1.1.1.1 Draft TOC | [5] 1.1.2.1 Draft target audience |  | [5] x.x.x.x Incorporate feedback in TOC and target audience | Etc.
[3] 1.1.2.1 Review target audience
SS+15
FS
FS
FS
FS
FS+15

## Schedule Baseline
Schedule Baseline | NOTE - LOCK this sheet once you complete it to protect your schedule baseline.
Project ID: | [insert project ID]
Project name: | [insert project name]
Project type: | [insert project type; i.e., product, software, marketing, infrastructure, operations, research and dev, event, training, merger and acquisition, compliance, environment, data, etc.]
Project start date: | [enter project start date]
Project end date: | [enter project end date]
Project sponsor: | [enter name of project sponsor]
Project manager: | [enter name of project manager]
Project coordinator: | [enter name of project coordinator]
Last update: | 2023-09-05
Baseline version # | 1
Percent complete: | 0%
| Task # | WBS code | % | Status | Task name | Duration (days) | Baseline start date | Baseline due date | Lead/Lag (days) | Assigned to | Effort (hrs.) | Effort completed | Effort remaining
| 1 | 1 | 0% |  | Project Name | 30 | [6 empty] | 0
| 2 | 1.1 | 0% |  | Concept proposal | 30 | [6 empty] | 0
| 3 | 1.1.1 | 0% |  | Theory of change (TOC) | 10 | [6 empty] | 0
| 4 | 1.1.1.1 | 0% | Not started | Draft TOC | 5 | 2023-02-05 | 2023-02-15 | 5 | Strategist | 16 |  | 16
| 5 | 1.1.1.2 | 0% | Not started | Review TOC | 3 | 2023-02-11 | 2023-02-16 | 2 | Sponsor, Support Strategist | 3 |  | 3
| 6 | 1.1.1.3 | 0% | Not started | Finalize TOC | 2 | 2023-02-17 | 2023-02-22 | 3 | Strategist | 4 |  | 4
| 7 | 1.1.2 | 0% |  | Target audience | 10 | [6 empty] | 0
| 8 | 1.1.2.1 | 0% | Not started | Draft target audience | 5 | 2023-02-23 | 2023-03-01 | 1 | Strategist | 8 |  | 8
| 9 | 1.1.2.2 | 0% | Not started | Review target audience | 3 | 2023-03-02 | 2023-03-07 | 2 | Sponsor, Support Strategist | 1 |  | 1
| 10 | 1.1.2.3 | 0% | Not started | Finalize target audience | 2 | 2023-03-08 | 2023-03-13 | 3 | Strategist | 1 |  | 1
| 11 | 1.1.3 | 0% |  | Proposed components | 10 | [6 empty] | 0
| 12 | 1.1.3.1 | 0% | Not started | Draft propose components | 5 | 2023-03-14 | 2023-03-19 | 0 | Strategist | 16 |  | 16
| 13 | 1.1.3.2 | 0% | Not started | Review proposed components | 3 | 2023-03-20 | 2023-03-25 | 2 | Sponsor, Support Strategist | 3 |  | 3
| 14 | 1.1.3.3 | 0% | Not started | Finalize proposed components | 2 | 2023-03-26 | 2023-03-31 | 3 | Strategist | 4 |  | 4
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
[8 empty] | 0 |  |  |  |  | 0
Formulas:
Baseline due date = Table3[[#This Row],[Baseline start date]]+Table3[[#This Row],[Duration (days)]]+Table3[[#This Row],[Lead/Lag (days)]]

## Current Schedule
Current Schedule
Project ID: | [insert project ID]
Project name: | [insert project name]
Project type: | [insert project type; i.e., product, software, marketing, infrastructure, operations, research and dev, event, training, merger and acquisition, compliance, environment, data, etc.]
Project start date: | [enter project start date]
Project end date: | [enter project end date]
Project sponsor: | [enter name of project sponsor]
Project manager: | [enter name of project manager]
Project coordinator: | [enter name of project coordinator]
Last update: | 2023-09-05
Baseline version # | 1
Percent complete: | 13.89%
| Task # | WBS code | % | Status | Task name | Duration (days) | Start date | Due date | Lead/Lag (days) | Assigned to | Baseline start date | Baseline finish date | Baseline finish variance | Effort (hrs.) | Effort completed | Effort remaining
| 1 | 1 | 13.89% |  | Project Name | 29 |  |  |  |  | 0 | 0 |  |  |  | 0
| 2 | 1.1 | 13.89% |  | Concept proposal | 29 |  |  |  |  | 0 | 0 |  |  |  | 0
| 3 | 1.1.1 | 41.67% |  | Theory of change (TOC) | 9 |  |  |  |  | 0 | 0 |  |  |  | 0
| 4 | 1.1.1.1 | 100% | Completed | Draft TOC | 4 | 2023-02-05 | 2023-02-14 | 5 | Strategist | 2023-02-05 | 2023-02-15 | -1 | 16 | 16 | 0
| 5 | 1.1.1.2 | 25% | In progress | Review TOC | 3 | 2023-02-11 | 2023-02-16 | 2 | Sponsor, Support Strategist | 2023-02-11 | 2023-02-16 | 0 | 3 | 1 | 2
| 6 | 1.1.1.3 | 0% | Not started | Finalize TOC | 2 | 2023-02-17 | 2023-02-22 | 3 | Strategist | 2023-02-17 | 2023-02-22 | 0 | 4 |  | 4
| 7 | 1.1.2 | 0% |  | Target audience | 10 |  | 1900-01-09 |  |  | 0 | 0 |  |  |  | 0
| 8 | 1.1.2.1 | 0% | Not started | Draft target audience | 5 | 2023-02-23 | 2023-03-01 | 1 | Strategist | 2023-02-23 | 2023-03-01 | 0 | 8 |  | 8
| 9 | 1.1.2.2 | 0% | Not started | Review target audience | 3 | 2023-03-02 | 2023-03-07 | 2 | Sponsor, Support Strategist | 2023-03-02 | 2023-03-07 | 0 | 1 |  | 1
| 10 | 1.1.2.3 | 0% | Not started | Finalize target audience | 2 | 2023-03-08 | 2023-03-13 | 3 | Strategist | 2023-03-08 | 2023-03-13 | 0 | 1 |  | 1
| 11 | 1.1.3 | 0% |  | Proposed components | 10 |  | 1900-01-09 |  |  | 0 | 0 |  |  |  | 0
| 12 | 1.1.3.1 | 0% | Not started | Draft propose components | 5 | 2023-03-14 | 2023-03-19 | 0 | Strategist | 2023-03-14 | 2023-03-19 | 0 | 16 |  | 16
| 13 | 1.1.3.2 | 0% | Not started | Review proposed components | 3 | 2023-03-20 | 2023-03-25 | 2 | Sponsor, Support Strategist | 2023-03-20 | 2023-03-25 | 0 | 3 |  | 3
| 14 | 1.1.3.3 | 0% | Not started | Finalize proposed components | 2 | 2023-03-26 | 2023-03-31 | 3 | Strategist | 2023-03-26 | 2023-03-31 | 0 | 4 |  | 4
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 |  |  | 0
Formulas:
Baseline start date = Table3[[#This Row],[Baseline start date]]
Baseline finish date = Table3[[#This Row],[Baseline due date]]
Due date = Table35[[#This Row],[Start date]]+Table35[[#This Row],[Duration (days)]]+Table35[[#This Row],[Lead/Lag (days)]]

## Data Validation (hidden)
Must have | Completed
Nice to have | In progress
OK if don’t have | Will not include
Requested