## Instructions
Instructions
Password protection for sheet and workbook to protect formulas is: 1234
Requirements
Requester | Add the name of the person who requested the requirement
Request date | Add the date the requester requested the requirement
Requirement | Add the description for the requirement
Importance | Use the dropdown menu to enter the importance level (note - conditional formatting will apply to must have and nice to have items).
Owner | Add the team member who is responsible for completing the requirement action items
Action item | Add the action item to be completed for the requirement
Status | Use the dropdown menu to enter the status of the owner complete the requirement action items
Status date | Add the date of the last status update
Additional notes | Use this column to share any other notes about the requirement
Scope Statement
Purpose | In this section, provide a brief overview of your publication project. Describe the purpose of the publication and what it aims to achieve. Include information about the target audience and the type of content you plan to publish.
Objectives | Clearly outline the specific objectives you want to accomplish with this publication project. Consider what you want to communicate to your audience and what impact you want to make. Your objectives should be measurable and aligned with the overall mission of the publication.
Deliverables | List all the tangible outputs or outcomes you expect to produce by the end of the project. Include both documents and final products that the team will deliver. For example, written content, designed layouts, and distribution plans.
Scope Boundaries | Identify the limits and boundaries of the project. What elements are out of scope and won't be addressed in this specific project? Clarify what the project won't be responsible for handling.
Assumptions | List any assumptions or prerequisites that need to be in place for the project to proceed successfully. These could include resources, access to experts, or specific content requirements.
Constraints | Outline the factors that may restrict the project's execution. Common constraints include time limitations, budgetary restrictions, or technology limitations.
Approval | Specify the stakeholders or decision-makers who need to review and approve the scope statement before the project can move forward. Ensure that all key parties are involved in this approval process.
Work Breakdown Structure (WBS)
Familiarize yourself with the scope statement to understand the objectives, deliverables, and overall scope of the project.
Start by identifying the major deliverables outlined in the scope statement. These are the primary results or outputs the project aims to produce.
For each major deliverable, break them down into smaller, manageable tasks or sub-tasks. These sub-tasks should be specific and concrete components of the major deliverables.
Organize the tasks into a hierarchical structure, breaking them down into manageable levels. The highest level represents the major deliverables, and each subsequent level breaks them down further into more detailed tasks.
The project name should be at the first level, the final deliverables should be the second level, the phase deliverables should be the third level, and the tasks and sub-tasks to complete each deliverable should be the lower level(s).
Use action-oriented language when defining tasks. Each task should be a clear action that can be completed within a reasonable timeframe.
Ensure that each task is distinct and doesn't overlap with other tasks. This will prevent confusion and duplication of effort during the project.
Collaborate with relevant team members and subject matter experts to gather input when creating the WBS. Their insights will help ensure the accuracy and comprehensiveness of the breakdown.
Assign unique identifiers (WBS codes) to each element of the WBS. This coding system will make it easier to reference and track tasks throughout the project.
Once the initial WBS is created, review and refine it to ensure all necessary tasks are included and appropriately organized.
Share the WBS with stakeholders and project sponsors to validate that it aligns with the approved scope and meets their expectations.
Throughout the project, maintain and update the WBS as necessary to reflect changes, additions, or modifications to the project scope.
You can use this template for your WBS, or consider using project management software to create and manage the WBS efficiently. Many tools offer features to visualize and track project tasks effectively.

## Requirements
Requirements
| Request date | Requester | Requirement | Importance | Owner | Action item | Status | Status Date | Additional notes
| 2023-02-23 | Jane | Publication should cover career advice, wellness tips, and personal finance insights. | Must have | Tom | Incorporate this design element into all designs | In progress | 2023-02-24
| 2023-02-23 | Jim | Main colors used should be from our branding guidelines. | Nice to have | Tom | Incorporate this design element into all designs | Requested | 2023-02-24
| 2023-02-23 | Sue | Use our images from the XYZ department outing throughout the publication. | OK if don’t have | Becky | None | Will not include | 2023-02-24 | We will actually use images from ABC outing instead.

## Scope Statement
Scope Statement
| Purpose | Our publication project aims to create an online magazine targeting young professionals interested in personal development, career growth, and lifestyle topics. The publication will offer insightful articles, interviews, and creative content to inspire our audience.
| Objectives | Develop a content strategy that covers career advice, wellness tips, and personal finance insights. Produce high-quality articles and visual content that resonate with our target audience. Design an engaging and user-friendly website layout to host the publication. Establish a regular publishing schedule to maintain audience engagement. Increase website traffic and engagement by 20% within six months.
| Deliverables | Content strategy document with topics, tone, and distribution plan. 20 well-researched and written articles based on the content strategy. Professionally designed website layout showcasing the publication's content. Six-month publishing calendar with planned article releases. Quarterly reports tracking website traffic and engagement metrics.
| Scope Boundaries | Generating revenue through direct sales or advertising is not part of this project. Marketing efforts beyond the distribution plan are outside the scope.
| Assumptions | We assume that a team of freelance writers will be available to create the content. We expect access to industry experts for interviews and advice columns.
| Constraints | The project budget is limited to $10,000. The entire project must be completed within six months.
| Approval | This scope statement requires approval from the marketing manager and the project sponsor before initiating the project.

## WBS
Work Breakdown Structure (WBS)

## Data Validation (hidden)
Must have | Completed
Nice to have | In progress
OK if don’t have | Will not include
Requested